## Sheet1
Builder - Repairs By Status
Request Number | Category | Address Street | State | Address City | Development | Status | Priority | Sub Contractor Name | Created Date | Deadline Date | Description
0435-0065891 | Electrical | 2785-C Howard Ave | SC | Myrtle Beach | Market Common | Open |  |  | 2019-09-21 16:46 |  | light over the shower and the center overhead light is not working
0435-0065892 | Carpeting | 2785-C Howard Ave | SC | Myrtle Beach | Market Common | Open |  |  | 2019-09-21 16:53 |  | cracked and not filled in
0435-0066034 | Doors | 2785-C Howard Ave | SC | Myrtle Beach | Market Common | Open |  |  | 2019-09-23 12:26 |  | Sticking and closing on opening and rubbing
0435-0066035 | Flooring | 2785-C Howard Ave | SC | Myrtle Beach | Market Common | Open |  |  | 2019-09-23 12:27 |  | wood exposed raw under certain floor boards and nicks in hardwood flooring
0435-0066037 | Carpentry | 2785-C Howard Ave | SC | Myrtle Beach | Market Common | Open |  |  | 2019-09-23 12:28 |  | Floor Molding not painted around door to toilet
0435-0066217 | Plumbing | 2785-C Howard Ave | SC | Myrtle Beach | Market Common | Open |  |  | 2019-09-24 16:21 |  | Kitchen sink faucet not working...
0435-0066314 | Windows | 2785-C Howard Ave | SC | Myrtle Beach | Market Common | Open |  |  | 2019-09-25 13:22 |  | Had professional window cleaners come because of the filthy condition of windows...paperwork still stuck to windows...spray paint, They went window by window with me.....
Severe scratches and grooves throughout house
0435-0066977 | Drywall | 2785-C Howard Ave | SC | Myrtle Beach | Market Common | Open |  |  | 2019-10-02 06:40 |  | caulking at joint of crown molding of crown not done
0435-0066978 | Landscaping | 2785-C Howard Ave | SC | Myrtle Beach | Market Common | Open |  |  | 2019-10-02 06:41 |  | plants outside of lower front windows and grass not being watered or cared for
0435-0066979 | Windows | 2785-C Howard Ave | SC | Myrtle Beach | Market Common | Open |  |  | 2019-10-02 06:43 |  | major scrapes and scratches on upper and lower panes throughout house...must be replaced as soon as possible
0435-0065541 | Drywall | 2785-C Howard Ave | SC | Myrtle Beach | Market Common | Open |  |  | 2019-09-17 07:34 |  | Marks of dirt and imperfections
0435-0065542 | Windows | 2785-C Howard Ave | SC | Myrtle Beach | Market Common | Open |  |  | 2019-09-17 07:35 |  | Left invoice on upper second floor window
Paint debris on windows through out
0435-0065639 | Carpentry | 2785-C Howard Ave | SC | Myrtle Beach | Market Common | Open |  |  | 2019-09-18 08:32 |  | handrail pulled away from wall...nails are exposed
0435-0065648 | Doors | 2785-C Howard Ave | SC | Myrtle Beach | Market Common | Open |  |  | 2019-09-18 09:47 |  | exposed nailheads all around doors...need covers
0435-0065807 | Doors | 2785-C Howard Ave | SC | Myrtle Beach | Market Common | Open |  |  | 2019-09-20 09:14 |  | The connection for the door to close is out of alignment....does not match up
0435-0065808 | Interior stairs | 2785-C Howard Ave | SC | Myrtle Beach | Market Common | Open |  |  | 2019-09-20 09:15 |  | The little hall light mounted on the wall is cracked
0435-0065809 | Drywall | 2785-C Howard Ave | SC | Myrtle Beach | Market Common | Open |  |  | 2019-09-20 09:17 |  | Do not have touch up paint
0435-0067203 | Lot drainage | 2785-C Howard Ave | SC | Myrtle Beach | Market Common | Open |  |  | 2019-10-05 08:16 |  | street floods even on a light rain day...difficult getting into garage or coming out.....
0435-0068334 | Brick work | 2785-C Howard Ave | SC | Myrtle Beach | Market Common | Open |  |  | 2019-10-17 09:17 |  | hole under the 1st overhang on the left...gaping space and hole under the went for the microwave..also underneath in the brick
0435-0068335 | Windows | 2785-C Howard Ave | SC | Myrtle Beach | Market Common | Open |  |  | 2019-10-17 09:18 |  | scratches on the french door nearest the street on the left upper pane
0435-0068680 | Carpentry | 2785-C Howard Ave | SC | Myrtle Beach | Market Common | Open |  |  | 2019-10-21 05:27 |  | 4th step up from landing exposed nail in left corner
0435-0065868 | Doors | 850 Rosa Cir | SC | Myrtle Beach | Market Common | Open |  |  | 2019-09-21 08:51 |  | Both French doors are warped (if you're facing the doors, it's the right side door in both instances),; however the set closest to the bathroom are more severely warped. The warping far exceeds the 1/4 " addressed in the warranty
0435-0067028 | Appliances | 7815 Monarch Dr | SC | Myrtle Beach | Papillon | Open |  |  | 2019-10-02 17:59 |  | Cover around the microwave oven falls off by itself all the time.
Requires some form of adhesion to the wall.
0435-0067029 | Windows | 7815 Monarch Dr | SC | Myrtle Beach | Papillon | Open |  |  | 2019-10-02 18:07 |  | There is paint and plaster on the exterior side of windows throughout the house.
Pointed this out to Keith on the Day 1 walk through of the house. He agreed that it needed to be addressed and said he would send someone to address it.
0435-0067030 | Doors | 7815 Monarch Dr | SC | Myrtle Beach | Papillon | Open |  |  | 2019-10-02 18:11 |  | Doors leading out to the balcony on the second and third floors to not close properly and need to be re-hung.
The doors have been that way for an extended period of time and as such, the frame where the door closes have been damaged on both floors. Deadbolt locks do not lock properly and are a security risk.
Pointed this out to Keith on the Day 1 walk through of the house. He agreed that it needed to be addressed and said he would send someone to address it.
0435-0067031 | Paint | 7815 Monarch Dr | SC | Myrtle Beach | Papillon | Open |  |  | 2019-10-02 18:14 |  | Crown moulding corners throughout the house were not painted properly & have separated. As well, there are placed throughout the house where the moulding has separated and need to be painted.
There was painting performed shortly after moving in, but they missed many spots and new separation between moulding pieces has occurred in many locations across the house.
Also, the frames and doors around the elevator on each level need to be painted. There is significant scuffing and damage around the door handle on each floor.
0435-0067033 | Doors | 7815 Monarch Dr | SC | Myrtle Beach | Papillon | Open |  |  | 2019-10-02 18:18 |  | Pocket doors do not operate effectively and need to be adjusted. They do not open well at all and once closed back in the pocket, they will not stay closed.
For all bedrooms on the 3rd floor.
0435-0067034 | Bathroom fixtures | 7815 Monarch Dr | SC | Myrtle Beach | Papillon | Open |  |  | 2019-10-02 18:20 |  | There is a cover on the vanity in the 1st floor bathroom that needs to be fixed.
There is a missing hook and the cover of the vanity simply falls off.
0435-0067036 | Interior trim | 7815 Monarch Dr | SC | Myrtle Beach | Papillon | Open |  |  | 2019-10-02 18:46 |  | There is open drywall holes that needs to be fixed and moulding around on the kitchen island has separated significantly from the drywall.
0435-0067037 | Caulking | 7815 Monarch Dr | SC | Myrtle Beach | Papillon | Open |  |  | 2019-10-02 18:48 |  | There are multiple locations throughout both bathrooms on the 3rd floor with large open gaps in caulking which need to be addressed.
0435-0067038 | Fireplaces | 7815 Monarch Dr | SC | Myrtle Beach | Papillon | Open |  |  | 2019-10-02 18:50 |  | There is a large gap between the floor & the fireplace mantle. Needs to be addressed.
0435-0067039 | Concrete | 7815 Monarch Dr | SC | Myrtle Beach | Papillon | Open |  |  | 2019-10-02 18:54 |  | There is an external drain - could be from an HVAC unit - that drains outside. where it drains out, there is concrete leftover at that spot. not sure why.
0435-0067040 | Concrete | 7815 Monarch Dr | SC | Myrtle Beach | Papillon | Open |  |  | 2019-10-02 18:56 |  | There is a drip drain outside of the house - could be from an HVAC unit - which drains out to concrete. Not sure why there is concrete there, but it is quite a mess and needs to be addressed.
Pointed this out to Keith on the Day 1 walk through of the house. He agreed that it needed to be addressed and said he would send someone to address it.